## Dashboard
📋 EVENT PROJECT TIMELINE & TASK MANAGER
From kickoff to wrap-up — every task, deadline, and milestone tracked.
TOTAL TASKS |  | COMPLETED |  | IN PROGRESS | NOT STARTED
19 |  | 0 |  | 0 | 19
OVERALL COMPLETION
0%
TASKS BY PHASE
Phase | Total | Done | % Done
Planning & Strategy | 3 | 0 | 0%
Venue & Logistics | 3 | 0 | 0%
Marketing & Promotion | 4 | 0 | 0%
Speaker / Talent | 1 | 0 | 0%
Production & AV | 1 | 0 | 0%
Day-Of Execution | 3 | 0 | 0%
Post-Event Wrap-Up | 4 | 0 | 0%

## Tasks
Task Master List
Status options: Not Started / In Progress / Complete / Blocked ¦ Priority: High / Medium / Low
# | Task Name | Phase | Owner | Due Date | Status | Priority | Dependencies | Notes
1 | Define event goals & objectives | Planning & Strategy | Event Lead |  | Not Started | High
2 | Set event date & confirm venue availability | Planning & Strategy | Event Lead |  | Not Started | High
3 | Create initial budget | Planning & Strategy | Finance Lead |  | Not Started | High
4 | Select & book venue | Venue & Logistics | Event Lead |  | Not Started | High | Task 2
5 | Arrange catering | Venue & Logistics | Ops Lead |  | Not Started | High | Task 4
6 | Book AV / tech team | Production & AV | Tech Lead |  | Not Started | High | Task 4
7 | Arrange transportation & parking | Venue & Logistics | Ops Lead |  | Not Started | Medium | Task 4
8 | Design event branding & collateral | Marketing & Promotion | Marketing |  | Not Started | High
9 | Launch event registration page | Marketing & Promotion | Marketing |  | Not Started | High | Task 8
10 | Email marketing campaign | Marketing & Promotion | Marketing |  | Not Started | Medium | Task 9
11 | Social media promotion | Marketing & Promotion | Marketing |  | Not Started | Medium | Task 9
12 | Confirm speakers / presenters | Speaker / Talent | Talent Lead |  | Not Started | High
13 | Prepare run-of-show document | Day-Of Execution | Coordinator |  | Not Started | High | All tasks
14 | Venue walkthrough with vendors | Day-Of Execution | Coordinator |  | Not Started | High
15 | Day-of staff briefing | Day-Of Execution | Coordinator |  | Not Started | High
16 | Post-event survey to attendees | Post-Event Wrap-Up | Marketing |  | Not Started | Medium
17 | Final budget reconciliation | Post-Event Wrap-Up | Finance |  | Not Started | High
18 | Vendor payment final | Post-Event Wrap-Up | Finance |  | Not Started | High
19 | Event debrief & lessons learned | Post-Event Wrap-Up | Event Lead |  | Not Started | Medium
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200